GOVERNMENT OF THE REPUBLIC OF SERBIA
PUBLIC PROCUREMENT OFFICE

MEDIUM-TERM PLAN
OF THE PUBLIC PROCUREMENT OFFICE
FOR THE PERIOD FROM 2022 TO 2024

Belgrade, January 2022

Table of Contents

[Table of Contents 2](#_Toc123149658)

[Abbreviations 3](#_Toc123149659)

[Introduction 4](#_Toc123149660)

[Information on the medium-term planning payer 5](#_Toc123149661)

[Competencies of the Public Procurement Office 6](#_Toc123149662)

[MEDIUM-TERM PLAN - a tabular view 8](#_Toc123149663)

[ATTACHMENTS: 28](#_Toc123149664)

[Plan of normative activities (Article 13 of the Decree on the methodology for the preparation of medium-term plans (“Official Gazette of the Republic of Serbia”, No. 8/19) 28](#_Toc123149665)

[Medium-term framework of expenses 29](#_Toc123149666)

Abbreviations

RS - Republic of Serbia

AS - Action plan

PPO - Public Procurement Office

LPPPC - Law on Public-Private Partnerships and Concessions CPPP - Commission for Public-Private Partnership MoE - Ministry of Economy

RB - Review Body

MFIN - Ministry of Finance

SAI - State Audit Institution

EU - European Union

CCIS - Chamber of Commerce and Industry of Serbia

CSOs - civil society organisations

USAID - US Agency for International Development

NALED - National Alliance for Local Economic Development

UNDP - United Nations Development Programme

JA - Judicial Academy

GPPs - Green public procurements

Introduction

The Law on the Planning System of the Republic of Serbia (“Official Gazette of the Republic of Serbia”, No. 30/18) introduced the obligation of drafting and submitting the medium-term plan also for the public administration authorities (Article 26 of the Law). The same article introduced the obligation to prepare and publish the medium-term plan by 31 January of the current year on the portal of the public administration.

The Decree on the methodology for the preparation of medium-term plans (“Official Gazette of the Republic of Serbia”, No. 8/19) prescribes the mandatory form and content of the medium-term plan, in accordance with which the Medium-Term Plan for the Office of Public Procurement was prepared. Annexes are published along with the Medium-Term Plan of the Office for Public Procurement, in accordance with the Decree.

Information on the medium-term planning payer

|  |  |
| --- | --- |
| Name of state authority: | Public Procurement Office |
| Seat:  | Gračanička 8, 11000 Belgrade |
| Address for service of mail:  | Nemanjina 22-26, 11000 Belgrade |
| Identification/registration number:  | 17418785 |
| Tax identification number: | 102027924 |
| E-mail for receipt of submissions: | office@ura.gov.rs |
| Website: | [www.uin.gov.rs](http://www.uin.gov.rs) |
| Phone: | 011/2888-712 |

The information booklet on the work of the Public Procurement Office is available to the public in electronic form at the website of the Public Procurement Office: https://www.ujn.gov.rs/o-nama/informator-o-radu/

Competencies of the Public Procurement Office

The Public Procurement Office is a special organisation that performs professional tasks in the field of public procurement, monitors the implementation of regulations on public procurement, adopts by-laws, monitors the implementation of public procurement procedures, controls the implementation of certain procedures, manages the Public Procurement Portal, prepares reports on public procurement, proposes measures to improve the public procurement system, provides professional assistance to clients and bidders, contributes to the creation of conditions for economical, efficient and transparent use of public funds in the public procurement process.

The regulations on state administration shall apply to the work and organisation of the Public Procurement Office, unless otherwise determined by the Law on Public Procurement (“Official Gazette of the Republic of Serbia”, No. 91/19).

The Public Procurement Office performs the following tasks:

prepares the strategy for the development and improvement of public procurement in the Republic of Serbia; monitors the implementation of public procurement regulations and prepares the annual report on the conducted monitoring;

submits a request for initiating misdemeanour proceedings for misdemeanours prescribed by this Law, submits a request for protection of rights and initiates the implementation of other appropriate procedures before the competent authorities when, based on monitoring, it notices irregularities in the application of public procurement regulations;

* participates in the drafting of laws and other regulations in the field of public procurement and adopts bylaws in the field of public procurement;
* gives opinions on the application of the provisions of this Law and other regulations in the field of public procurement;

provides professional assistance, prepares guidelines, manuals, as well as other publications in the field of public procurement and ensures that they are equally accessible to contracting authorities and economic operators free of charge;

collects statistical and other data on conducted procedures, concluded public procurement contracts and prepares a special annual report on public procurement;

prescribes the procedure and conditions for obtaining a certificate for a public procurement officer and keep a register of public procurement officers; manages the Public Procurement Portal;

undertakes the necessary activities related to the negotiations on accession to the European Union, in the field of public procurement;

cooperates with domestic and foreign institutions and experts in the field of public procurement in order to improve the public procurement system;

cooperates with other state bodies and organisations, bodies of territorial autonomy and local self-government; performs other tasks, in accordance with the law.

ORGANISATIONAL STRUCTURE OF THE PUBLIC PROCUREMENT OFFICE



MEDIUM-TERM PLAN - a tabular view

|  |
| --- |
| A TABULAR VIEW OF THE MEASURES AND ACTIVITIES OF THE OFFICE FOR PUBLIC PROCUREMENT FOR THE PERIOD 2022-2024 |
| Goal 1: Further development of a modern and efficient public procurement system  |
| Planning document from which the goal was taken: Public Procurement Development Programme for the period from 2019 to 2023 |
| Indicator(s) at the level of the goal (effect indicator) | Unitof measurement | Source of check | Initial value | Baselineyear | Target value in the last year  | Last year of validity of the planning document |
| Annual Progress Report of the European Commission for the Republic of Serbia | 0 - No progress1-Partial progress2- Significant progress | Annual Progress Report of the European Commission for the Republic of Serbia | 1 | 2021 | 2 | 2023 |
| Development of functionalities of the Public Procurement Portal | 1. - not achieved
2. -

achieved | Anual report of the Public Procurement Office | 1 | 2021 | 1 | 2023 |

Objective 1.1: Increasing the efficiency and economy of public procurement procedures

|  |
| --- |
| Planning document from which the goal was taken: Public Procurement Development Programme in the Republic of Serbia for the period from 2019 to 2023, estabished by the Medium-Term Plan, Reform Programme of Public Finances Management AP for the period 2021-2025 |
| Budget programme taking the objective (code and name): |
| Indicator(s) at the level of the objective (outcome indicator) | Unit of measurement | Sourceof check | Baseline value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Averageduration ofopenprocedure(days) | Number | Annual Report on Public Procurement Procedures of the PPO | 48[[1]](#footnote-1) | 2021 | 47 | 47 | 47 |
| Objective 1.2: Strengthening competition on the public procurement market Planning document from which the goal was taken: Public Procurement Development Programme in the Republic of Serbia for the period from 2019 to 2023, estabished by the Medium-Term Plan of Reform Programme of Public Finances Management for the period 2021-2025 |
| Budget programme taking the objective (code and name): |
| Indicator(s) at the level of the objective (outcome indicator) | Unit of measurement | Sourceof check | Baseline value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Average number of offers under the public procurement procedure | Number | Annual Report on Public Procurement Procedures of the PPO | 2.5[[2]](#footnote-2) | 2020 | 2.6 | 2.6 | 2.6 |
| Objective | .3: Reduction of the risk of irregularities in the public procurement system  |  |  |
| Planning document from which the goal was taken: Public Procurement Development Programme in the Republic of Serbia for the period from 2019 to 2023, estabished by the Medium-Term Plan |
| Budget programme taking the objective (code and name): |
| Indicator(s) at the level of the objective (outcome indicator) | Unitof measurement | Sourceof check | Baseline value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Numberof procedures over which the monitoring was conducted | Number | Annual report on the conducted monitoring of the PPO | 258[[3]](#footnote-3) | 2021 | 500 | 500 | 500 |
| Objective 1.4: Promotion and encouragement of environmental and social aspects in public procurement and innovations |
| Planning document from which the goal was taken: Public Procurement Development Programme in the Republic of Serbia for the period from 2019 to 2023, estabished by the Mid-Term Plan |
| Budget programme taking the objective (code and name): |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Indicator(s) at the level of the objective (outcome indicator) |  Unit of measurement | Sourceof check | Baseline value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Numberconductedpublicprocurementsby applyingecologicalaspects | Number | Annual Report on Public Procurement Procedures of the PPO | 650[[4]](#footnote-4) | 2021 | 700 | 720 | 740 |
| Numberconductedpublicprocurementsby applyingsocial aspects | Number | Annual Report on Public Procurement Procedures of the PPO | 86[[5]](#footnote-5) | 2021 | 90 | 100 | 110 |

|  |
| --- |
| Measure 1: Improving the legal framework |
| Planning document from which the measure was taken: Public Procurement Development Programme in the Republic of Serbia for the period from 2019 to 2023, established by the Medium-Term Plan, Reform Programme of Public Finances Management AP for the period 2021-2025 |
| Implementation period: 2022 | Type of measure: Regulatory measure |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Indicator(s) at the level of the measure (output indicator) | Unit of measurement | Source of check | Initial value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Amendments to the PPLPC in application | Under preparation - 0 applied - 1 | “Official Gazette of the Republic of Serbia” | 0 | 2021 |  | 1 |  |
| Activity name | Implementing entity (authority department) | Deadline for activity completion | Source of financing | Total estimated financial resources by source in 000 dinars |
| In 2022 | In 2023 | In 2024 |
| 1.1.1 Development and adoption of a public policy document for the development of public procurement for the period 2024-2028 | PPO | 4th quarter of 2023 | RS budgetInternational assistance |  | 0612 - programme(regularallocations) |  |
| 1.1.2 Proposing amendments to the PPLPC  | ME | 4th quarter of 2022 | RS budget |  |  |  |

|  |
| --- |
| Planning document from which the measure was taken: Public Procurement Development Programme in the Republic of Serbia for the period from 2019 to 2023, established by the Medium-Term Plan |
| Implementation period: 2022 | Type of measure: Informative and educational measure |
| Indicator(s) at the level of the measure (output indicator) | Unit of measurement | Sourceof check | Baseline value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Number of employed persons inPublic Procurement Office[[6]](#footnote-6) | Number | Annual Report on Public Procurement of the PPO | 44 | 2021 | 46 | 48 | 50 |
| Numberof cetified public procurement officers | Number | Annual Report on Public Procurement of the PPO | 4845[[7]](#footnote-7) | 2021 | 4950 | 5100 | 5200 |
| Activity name | Implementing entity (authority department) | Deadline for activity completion | Sourceof financing | Total estimated financial resources by source in 000 dinars |
| In 2022 | In 2024In 2023  |

Measure 2: Strengthening the institutional framework

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1.2.1Organising the examination for Public Procurement Officers | PPO | 4th quarter of 2023.8 | RS budget | 0612 - programme (regular allocations) | 0612 - programme (regular allocations) | 0612 - programme(regularallocations) |
| 1.2.2 Training for Preparation of Taking the Examination for Public Procurement Officers | PPONALED | 4th quarter of 2022 | RS budgetInternational assistance | 0612 - programme(regularallocations) |  |  |
| 1.2.3Organising workshops to harmonise the positions of the PPO, RB, MFIN and SAI regarding the new LPP  | PPORBMFINSAIUSAID | 4th quarter of 2023.9 | RS budgetInternational assistance | 0612 - programme(regularallocations)EUR 2,000 (240,000.00RSD) | 0612 - programme (regular allocations) |  |
| 1.2.4 Training of the Police, Public Prosecutor’s Office, SAI and other institutions in the  | PPOUSAIDUNDP | 4th quarter of 2023.10 | RS budgetInternational assistance | 0612 - programme(regularallocations) | 0612 - programme (regular allocations) |  |

1. Continuous activity that is regularly carried out several times during the year.
2. Continuous activity that is regularly carried out several times during the year.
3. Continuous activity that is regularly carried out several times during the year.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| field of public procurement |  |  |  | EUR 2,000 (RSD 240,000.00) |  |  |
| Measure 3: Improvement of electronic public procurement |
| Planning document from which the measure was taken: Public Procurement Development Programme in the Republic of Serbia for the period from 2019 to 2023, estabished by the Medium-Term Plan, Reform Programme of Public Finances Management AP for the period 2021-2025 |
| Implementation period: 2022 | Type of measure: Measure of provision of goods and services by participants in the planning system |
| Indicator(s) at the level of the measure (output indicator) |  Unitof measurement | Sourceof check | Initial value | Baseline year | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Increased number of new functionalities on the Public Procurement Portal | Number | Portalpublicprocurements | 1011 | 2021 | 13 | 14 | 15 |
| Activity name | Authority(authority’s department) implementing the activity |  Deadline for activity completion | Sourceof financing | Total estimated financial resources by source in 000 dinars |
| In 2022 | In 2023 | In 2024 |

11 <https://jnportal.ujn.gov.rs/konzola>

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1.3.1 Development of technical specification for the development of new functionalities on the Public Procurement Portal  | PPO | 4th quarter of 2022 | RS budgetInternational assistance | 0612 - programme (regular allocations)EUR 15,000 (RSD 1,800,000.00) |  |  |
| 1.3.2. English translation of video instructions for users of the Public Procurement Portal | PPONALED | 4th quarter of 2022 | RS budgetInternational assistance | 0612 - programme(regularallocations)EUR 500 (RSD 60,000.00) |  |  |
| 1.3.3 Development of the mobile application of the Procurement Portal for iOS and Android mobile platforms | PPONALED | 4th quarter of 2022 | RS budgetInternational assistance | 0612 - programme(regularallocations) |  |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | EUR 20,000 (2,400,000.00RSD) |  |  |
| Measure 4: Strengthening administrative capacities and education |
| Planning document from which the measure was taken: Public Procurement Development Programme in the Republic of Serbia for the period from 2019 to 2023, estabished by the Medium-Term Plan, Reform Programme of Public Finances Management AP for the period 2021-2025 |
| Implementation period: 2022 | Type of measure: Informative and educational measure |
| Indicator(s) at the level of the measure (output indicator) | Unit of measurement | Source of check | Initial value | Baseline year | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Numberof organised trainings during the year | Number | Website of the PPO | 812 | 2021 | 8 | 8 | 8 |
| Activity name | Implementing entity (authority department) | Deadline for activity completion | Sourceof financing | Total estimated financial resources by source in 000 dinars |
| In 2022 | In 2023 | In 2024 |
| 1.4.1Development of new models of tender documentation | PPONALED | 4th quarter of 2022 | RS budget | 0612 - programme (regular allocations)EUR 20,000 (RSD 2,400,000.00) |  |  |

12 The data of the PPO as of 31 December 2021.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| in a in accordance with the Law on Public Procurement  |  |  | International  |  |  |  |
|  |  | assistance |  |  |  |
| 1.4.2 | PPO |  | RS budget | 0612 - programme |  |  |
| Promotion of the tender documentation model | CCIS | 4th quarter of 2022 |  | (regular allocations) |  |  |
| NALED | International assistance | EUR 1,000 (RSD 120,000.00) |  |  |
|  |  |  | RS budget | 0612 - programme |  |  |
| 1.4.3 Development of a model of internal | PPO | 4th quarter of 2022 |  | (regular allocations) |  |  |
| acts of the contracting authority | NALED | International assistance | EUR 5,000 (RSD 600,000.00) |  |  |
| 1.4.4 Development of methodology on the basis of whichwill be monitoredexecution of public procurements procurements |  |  | RS budget | 0612 - programme |  |  |
| MFIN | 4th quarter of 2022 | (regular allocations) |  |  |
|  |
| PPO |  |  |  |  |
| NALED |  | International assistance | EUR 8,000  |  |  |
|  |  | (RSD 960,000.00) |  |  |
| 1.4.5 | PPO |  | RS budget | 0612 - programme |  |  |
| Organising training for contracting authorities and bidders | CCISUNDP | 4th quarter of 2024.[[8]](#footnote-8) | International assistance | (regular allocations) | 0612 - programme (regular allocations) | 0612 - programme (regular allocations) |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | EUR 3,000 (RSD 360,000.00) |  |  |
| 1.4.6Organising a seminar on the application of environmental aspects in public procurement procedures | PPOCCISUNDPNALED | 4th quarter of 2022 | RS budgetInternational assistance | 0612 - programme (regular allocations)EUR 1,000 (RSD 120,000.00) |  |  |
| 1.4.7Organising a seminar on the application of social aspects in public procurement procedures | PPOCCISNALED | 4th quarter of 2022 | RS budgetInternational assistance | 0612 - programme (regular allocations)EUR 1,000 (RSD 120,000.00) |  |  |
| 1.4.8.Organising trainings for micro, small and medium-sized enterprises  | PPOCCISUNDP | 4th quarter of 2022 | RS budgetInternational assistance | 0612 - programme (regular allocations)EUR 2,000 (RSD 240,000.00) |  |  |

Goal 2: Anti-corruption

Transitional measure 2.1: Serbia implements and evaluates the impact of measures taken with the aim of reducing corruption in vulnerable areas (health, taxes, customs, education, local self-government, privatisation, public procurement and the police), undertakes corrective measures where necessary and organises initial records of a measurable reduction in the level of corruption in the aforementioned areas.

Planning document from which the goal was taken: AP for Chapter 23 - judiciary and fundamental rights

Budget programme taking the objective (code and name):

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Indicator(s) at the level of the goal (outcome indicator) | Unit of measurement | Sourceof check | Initial value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Records of a measurable reduction in the level of corruption have been established. | 1. NO
2. YES
 | 1. European Commission’s positive assessment on Serbia’s progress 2. Annual Surveillance Report of the PPO,Annual report of the RB and Annual report of the SAI | 0 | 2021 |  | 1 |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 3. Number of initiated and completed torts and other procedures related to violation of the Law onPublicProcurement |  |  |  |  |  |
| Activity name | Implementing entity (authority department) | Deadline for activity completion | Sourceof financing | Total estimated financial resources by source in 000 dinars |
| In 2022 | In 2023 | In 2024 |
| 2.1.1 Monitoring of measures related to the implementation of supervision and control in public procurement. | PPORBMFIN | Continually,publicannually | RS budget | 0612 - programme(regularallocations) | 0612 - programme(regularallocations) | 0612 - programme(regularallocations) |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1.2 Carry out trainings for police members, prosecutors and judges in order to process the cases of corruption in public procurements more efficiently (compatible with the Strategy of Financial Investigations).  | PPO |  |  | 0612 -  | 0612 -  | 0612 -  |
| RB | Continually | RS budget | programme(regular | programme(regular | programme(regular |
| JA |  |  | allocations) | allocations) | allocations) |

|  |
| --- |
| Goal 3: Support for the implementation of green public procurement and environmental protection instruments |
| Planning document from which the goal was taken: Established by the Medium-Term Plan |  |  |
| Budget programme taking the objective (code and name): |
| Indicator(s) at the level of the objective (outcome indicator) |  Unit of measurement | Sourceof check | Initial value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Number of annual additional trainings/seminars and expert consultations in the field of GPPs | Number | ReportsMEPPPO | 1 | 2021 | 2 | 2 | 2 |
| Measure 3.1: Defining priority groups of goods, services and works for the Republic of Serbia for the application of green public procurement |
| Institution responsible for implementation: Ministry of Environmental Protection |

|  |
| --- |
| Implementation period: 2022 - 2024 Type of measure: Informative and educational measure |
| Indicator(s) at the level of the measure (output indicator) | Unit of measurement | Source of check | Initial value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Selected priority groups of goods, services and works for the application of GPPs | Yes/No | Reports of the MEP and PPO | No | 2021 |  | Yes |  |
| Name activities | Implementing entity (authority department) | Authorities partners implementing activities | Deadline for activity completion | Sourceof financing | Total estimated financial resources by source in 000 dinars |
| In 2022 | In 2023 | In 2024 |
| 3.1.1 Analysis of the potential of the application of GPPs in certain groups of goods, services and works | MEP | PPONALED | 2023 | RS budgetInternational assistance |  | 0612 - programme (regular allocations) |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1.2 Expert consultations with interested parties for individual groups of goods, services and works | MEP | PPOCCISNALED | 2023 | RS budgetInternational assistance |  | 0612 - programme(regularallocations) |  |
| 3.1.3 Development and publication of a list of groups of goods, services and works with priorities for implementation in the RS | MEP | PPONALED | 2023 | RS budgetInternational assistance |  | 0612 - programme(regularallocations) |  |
| Measure 3.2: Additional affirmation of GPPs and development of a guideline |
| Institution responsible for implementation: Ministry of Environmental Protection |
| Implementation period: 2022 - 2024 Type of measure: Informative and educational measure |
| Indicator(s) at the level of the measure (output indicator) | Unit of measurement | Source of check | Initial value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| Total number of produced additional guides in the field of GPPs | Number | Website of the MEP and PPO | 2 | 2021 | 3 | 4 | 5 |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Numberof seminars and/or trainings implemented in the field of GPPs per year | Number | Reports of the MEP and PPO from trainings | 1 | 2021 | 2 | 2 | 2 |
| Name activities | Implementing entity (authority department) | Authorities partners implementing activities | Deadline for activity completion | Sourceof financing | Total estimated financial resources by source in 000 dinars |
| In 2022 | In 2023 | In 2024 |
| 3.2.1 Supplementing the website of the Ministry of Education and Culture with a special section for GPPs | MEP | PPONALEDUNDP | 2022 | RS budgetInternational assistance | 0612 - programme(regularallocations) |  |  |
| 3.2.2 Development of additional guides for the application of GPPs | MEP | PPONALEDUNDPUSAID | 2024 | RS budgetInternational assistance |  |  | 0612 - programme(regularallocations) |

|  |
| --- |
| Measure 3.3: Development of criteria for green public procurement in the Serbian language (on the basis of available criteria for green public procurement in the EU, for appropriate groups of goods, services and works) |
| Institution responsible for implementation: Ministry of Environmental Protection |
| Implementation period: 2022 - 2024 Type of measure: Informative and educational measure |
| Indicator(s) at the level of the measure (output indicator) | Unit of measurement | Source of check | Initial value | Baselineyear | Target value in 2022 | Target value in 2023 | Target value in 2024 |
| The total number of documents prepared for the criteria for GPPs for the respective groups of goods, services and works | Number | Website of the MEP and PPO | 0 | 2021 | 6 | 10 | 18 |
| Name activities | Implementing entity (authority department) | Authorities partners implementing activities | Deadline for activity completion | Sourceof financing | Total estimated financial resources by source in 000 dinars |
| In 2022 | In 2023 | In 2024 |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.3.1Transposition and adjustment of EU criteria for green public procurement for selected groups of goods, services and works | MEP | PPONALED | 2024 | RS budgetInternational assistance |  |  | 0612 - programme(regularallocations) |
| 3.3.2Presentation of published criteria for GPPs tointerested parties | MEP | PPOCCISNALED | 2024 | RS budgetInternational assistance |  |  | 0612 - programme(regularallocations) |

Number: 110-00-4/2020-1 DIRECTOR [*signature*]

In Belgrade, dated 31 January 2022 Sandra Damčević

 [*stamp: Republic of Serbia, Public Procurement Office, Belgrade*]

ATTACHMENTS:

Plan of normative activities (Article 13 of the Decree on the methodology for the preparation of medium-term plans (“Official Gazette of the Republic of Serbia”, No. 8/19)

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Normativeactivities(NA) | Measure for the implementation of which NA isa precondition | AuthorityProponentof regulations | Typeof regulations | Legal basis | The quarter in which the regulation is submitted to the Government or the Minister for adoption, approval, or determination of the proposal | ConnectionwithNPAA |
| ACTS ADOPTED BY THE GOVERNMENT |
| Action plan for 2022 for the implementation of the Public Procurement Development Programme for 2022 |  | PPO |  | Article 38, paragraph 1 Law on the Planning System of the Republic of Serbia (“Official Gazette of the Republic of Serbia”, No. 30/18), Article 43, paragraph 3 Law on Government (“Official Gazette of the Republic of Serbia”, Nos. 55/05, 71/05 - correction, 101/07, 65/08, 16/11, 68/12 - Constitutional Court, 72/12, 7/14 - Constitutional Court, 44/14 and 30/18 - amending law), | 1/2022. | No |
| Action plan for 2022 for the implementation of the Programme  |  | PPO |  | Article 38, paragraph 1 Law on the Planning System of the Republic of Serbia (“Official Gazette of the Republic of Serbia”, No. 30/18), Article 43, paragraph 3 Law on the Government (“Official Gazette of the Republic of Serbia”, No.  | 4/2022. | No |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Public Procurement Development Programme for 2023  |  |  |  | 55/05, 71/05 - corr., 101/07, 65/08, 16/11,68/12 - Constitutional Court, 72/12, 7/14 - Constitutional Court, 44/14 and 30/18 - amending law) |  |  |
| Strategydevelopment publicprocurementsperiod2024-2028  |  | PPO |  | Article 38, paragraph 1 Law on the Planning System of the Republic of Serbia (“Official Gazette of the Republic of Serbia”, No. 30/18). | 4/2023. | No |

Medium-term framework of expenses

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Programme | Programme activity or project | Measure /Activity | 2022 Provided means (RSD 000) | 2023 Planned means (RSD 000) | 2024 Planned means (RSD 000) |
| 0612 - Development of the systemandprotection of rights in public procurement procedures | 0001 - Development and monitoring of the public procurement system**7003 – Public administration reform**  |  | 89,59586,784 | 67,507 | 67,507 |

1. Data from the Public Procurement Portal as of 31 December 2021. [↑](#footnote-ref-1)
2. Data from the Public Procurement Portal as of 31 December 2021. [↑](#footnote-ref-2)
3. Data from the PPO as of 31 December 2021. [↑](#footnote-ref-3)
4. Data from the Public Procurement Portal. [↑](#footnote-ref-4)
5. Data from the Public Procurement Portal. [↑](#footnote-ref-5)
6. The number of employees in the PPO includes permanent and fixed-term employees, as well as persons engaged through contracts (work outside the employment relationship) as of 31 December 2021. [↑](#footnote-ref-6)
7. The data from the Register of Public Procurement Officers kept by the PPO as at 31 December 2021. [↑](#footnote-ref-7)
8. 13Continuous activity that is regularly carried out several times during the year. [↑](#footnote-ref-8)