Based on Article 38, paragraph 1 of the Law on Planning System of the Republic of Serbia (“Official Gazette of the RS“, No. 30/18),

the Government hereby adopts the following

ACTION PLAN FOR 2026 FOR THE

IMLEMENTATION OF THE PUBLIC PROCUREMENT DEVELOPMENT PROGRAMME IN THE REPUBLIC OF SERBIA FOR THE PERIOD 2024 – 2028

I. INTRODUCTION

The Public Procurement Development Programme in the Republic of Serbia for the period 2024–2028 (“Official Gazette of the RS”, No. 68/24 – hereinafter referred to as: the Programme), together with the Action Plan for 2026 for the implementation of the Programme, represents a further enhancement of the results achieved in the public procurement system during the period 2019–2023.

To further implement the Programme, the Government adopts the Action Plan for 2026 for the Implementation of the Public Procurement Development Programme in the Republic of Serbia for the period 2024–2028 (hereinafter referred to as: the Action Plan).

The basis for adopting the Programme and this Action Plan is set out in two planning documents.

1) The National Programme for the Adoption of the Acquis of the European Union 2024–2027 (NPAA), specifically the section relating to Chapter 5 – Public Procurement, under the plans for strengthening institutional and administrative capacities and the measure “Improvement of the strategic framework in the field of public procurement”;

The Public Finance Management Reform Programme for the period 2021–2025 (“Official Gazette of the RS”, Nos. 70/21 and 116/23), specifically within Specific Objective 2. “Efficient collection and management of budget funds”, and Measure 2.5. “Improvement of the electronic public procurement system”.

In view of the objectives and measures defined by the Programme, as well as the activities set out in the action plans for its implementation for 2024 and 2025, and given that their implementation has contributed to the development of the public procurement system in the previous period, it has been assessed those efforts should continue in this direction in the coming period, as the planned activities remain largely unchanged.

All activities defined in this Action Plan contribute to achieving the Programme’s general and specific objectives and should ultimately lead to the fulfilment of all the criteria for the closure of Chapter 5 – Public Procurement.

II. BRIEF OVERVIEW OF RESULTS ACHIEVED DURING THE VALIDITY PERIOD OF THE ACTION PLAN FOR  2025

Based on the analysis of the implementation of the Programme’s 2025 Action Plan, it can be concluded that over 90% of the planned activities were fully implemented within the established timeframe. Activities that were not implemented under the 2025 Action Plan, such as “Proposing amendments to the LPPPC”, have been included in the 2026 Action Plan.

With regard to outcome indicators at the level of specific objectives and result indicators at the level of measures, the Public Procurement Office (hereinafter:  referred to as: the PPO) has achieved most of the planned targets. For those not yet fulfilled, the PPO will endeavour to achieve them fully within this action plan and in future annual planning documents in the field of public procurement.

List of abbreviations used in this Action Plan:

| APC | Agency for Prevention of Corruption |
| --- | --- |
| BV | Baseline value |
| CPC | Commission for Protection of Competition |
| EC | European Commission |
| EU | European Union |
| LPPPC | Law on Public-Private Partnerships and Concessions |
| MoF | Ministry of Finance |
| MoE | Ministry of Economy |
| SMEs | Small and Medium Enterprises |
| NALED | National Alliance for Local Economic Development |
| PPL | Law on Public Procurement |
| PPO | Public Procurement Office |
| PPP | Public-Private Partnership |
| PPP Commission | Commission for Public-Private Partnerships |
| RC | Republic Commission for the Protection of Rights in Public Procurement Procedures |
| RS | Republic of Serbia |
| SCCI | Serbian Chamber of Commerce and Industry |
| UNDP | United Nations Development Program |
| TV | Target value |

III. OBJECTIVES, MEASURES AND ACTIVITIES

| ACTION PLAN FOR 2026 FOR THE IMLEMENTATION OF THE PUBLIC PROCUREMENT DEVELOPMENT PROGRAMME IN THE REPUBLIC OF SERBIA FOR THE PERIOD 2024-2028 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GENERAL OBJECTIVE: Further development and strengthening of a sustainable and fair public procurement system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Title: |  |  |  |  | Action Plan for 2026 for the Implementation of the Public Procurement Development Programme of the Republic of Serbia |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for monitoring and controlling the implementation: |  |  |  |  | PPO |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Public policy document for which the Action Plan is drawn up |  |  |  |  | Public Procurement Development Programme in the Republic of Serbia for the period 2024-2028 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overarching public policy document |  |  |  |  | NPAA for the period 2024-2027 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GENERAL OBJECTIVE 1: FURTHER DEVELOPMENT AND STRENGTHENING OF A SUSTAINABLE AND FAIR PUBLIC PROCUREMENT SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at general objective level (outcome indicator) | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  |  |  | Baseline year |  | 2026 |  |  |
| EC assessment of progress in Chapter 5 – Public procurement and fulfilment of all criteria set out in this Chapter | No progress/Limited progress/Some progress/Good progress/Very good progress |  |  |  | EC Annual Progress Report |  |  |  | Limited progress |  |  |  |  | 2025 |  | Some progress |  |  |
| SPECIFIC OBJECTIVE 1.1: INCREASING ECONOMY AND COMPETITIVENESS IN PUBLIC PROCUREMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  |  |  | Baseline year |  | Target value 2026 |  |  |
| SMEs participation in the number of contracts concluded | Percent (%) |  |  |  | PPO Annual Report on Public Procurement |  |  |  | 72.3 |  |  |  |  | 2025 |  | 73 |  |  |
| Inclusion of criteria for awarding contracts that are not solely based on price. | Percent (%) |  |  |  | PPO Annual Report on Public Procurement |  |  |  | 10.39 |  |  |  |  | 2025 |  | 10.5 |  |  |
| Measure 1.1.1: Improving the regulatory framework and strengthening practise in the area of PPP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: MoE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  | Measure type: Regulatory / Informative-Educational |  |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| 01– revenues from the budget/ regular allocations |  |  |  | 1508/0002 |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  |  |  | Baseline year |  | Target value 2026 |  |  |
| Adoption of the Law Amending the PPPCL | Yes/No |  |  |  | ”Official Gazette of the RS” |  |  |  | No |  |  |  |  | 2025 |  | Yes |  |  |
| Name of the activity | Deadline for completion of activities |  |  |  | Institution responsible for implementation |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |
| 1.1.1.1. Proposal of amendments to the LPPPC | Q4 2026 |  |  |  | MoE |  |  | PPP Commission |  |  |  | Revenues from the budget/regular allocations |  | 1508/0002 |  | - |  |  |
| Measure 1.1.2: Strengthening institutional capacities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: PPO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  | Measure type: Institutional-Managerial-Organisational |  |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| Revenues from the budget/regular allocations. |  |  |  | 0612/0001 |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| Donor funds* |  |  |  | / |  |  |  |  | 960 |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  |  |  | Baseline year |  | Target value 2026 |  |  |
| Total number of employees in the Public Procurement Office | Number |  |  |  | Information Booklet of the PPO |  |  |  | 37 |  |  |  |  | 2025 |  | 39 |  |  |
| Name of the activity | Deadline for completion of activities |  |  |  | Institution responsible for implementation |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |
| 1.1.2.1. Organisation of training and professional development for staff in key public procurement institutions | Q4 2026 |  |  |  | PPO |  |  | RC PPP Commission CPC NALED EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 960 |  |  |
| Measure 1.1.3: Strengthening the administrative capacity of contracting authorities and economic operators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: PPO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  | Measure type: Informative-Educational |  |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| Revenues from the budget/regular allocations. |  |  |  | 0612/0001 |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| *Donor funds |  |  |  | / |  |  |  |  | 11,320 |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  |  |  | Baseline year |  | Target value 2026 |  |  |
| Total number of certified public procurement officers | Number |  |  |  | PPO Annual Report on Public Procurement |  |  |  | 5790 |  |  |  |  | 2025 |  | 5,850 |  |  |
| Name of the activity | Deadline for completion of activities |  |  |  | Institution responsible for implementation |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |
| 1.1.3.1. Organisation of training for contracting authorities and economic operators in the field of public procurement | Q4 2026 |  |  |  | PPO |  |  | NALED SCCI EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 960 |  |  |
| 1.1.3.2. Organisation of training for the preparation of public procurement officers for the certification exam | Q4 2026 |  |  |  | PPO |  |  | EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 960 |  |  |
| 1.1.3.3. Organisation of a roundtable with key institutions in the public procurement system and representatives of economic operators | Q4 2026 |  |  |  | PPO |  |  | SCCI |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 480 |  |  |
| 1.1.3.4. Analysis of barriers to participation of economic operators in public procurement procedures | Q4 2026 |  |  |  | PPO |  |  | NALED |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 1,200 |  |  |
| 1.1.3.5. Development of a methodology for determining the estimated value of public procurement | Q4 2026 |  |  |  | PPO |  |  | EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 1,200 |  |  |
| 1.1.3.6. Organisation of a workshop to present the methodology for estimating the value of public procurement to contracting authorities | Q4 2026 |  |  |  | PPO |  |  | EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 480 |  |  |
| 1.1.3.7. Organisation of training on market research in public procurement to enhance competition in procurement procedures | Q4 2026 |  |  |  | PPO |  |  | EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 960 |  |  |
| 1.1.3.8. Development of guidance/recommendations for economic operators for participation in public procurement procedures | Q4 2026 |  |  |  | PPO |  |  | NALED |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 1,000 |  |  |
| 1.1.3.9. Development of a practical tool (guidelines, instructions or similar) to enhance the capacities of local self-government units in relation to anti-corruption measures in public procurement | Q4 2026 |  |  |  | PPO |  |  | EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 1,200 |  |  |
| 1.1.3.10. Organisation of training for local self-government units on anti-corruption measures in public procurement | Q4 2026 |  |  |  | PPO |  |  | EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 2,880 |  |  |
| Measure 1.1.4: Improvement of the e-Procurement system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: PPO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  |  | Measure type: Supply of goods and provision of services |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| Revenues from the budget/regular allocations. |  |  |  | 0612/0001 |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| *Donor funds |  |  |  | / |  |  |  |  | 14,460 |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  | Baseline year |  | Target value 2026 |  |  |  |
| Total number of new versions of the Public Procurement Portal implemented |  | Number |  |  |  | Public Procurement Portal |  |  |  | 21 |  |  | 2025 |  | 23 |  |  |  |
| Name of the activity |  | Deadline for completion of activities | Institution responsible for implementation |  |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |  |
| 1.1.4.1. Development of technical specifications for the introduction of new functionalities on the Portal |  | Q4 2026 | PPO |  |  |  | EU/UNDP |  |  |  | *Donor funds |  |  |  | 2,700 |  |  |  |
| 1.1.4.2. Development of new functionalities on the Public Procurement Portal |  | Q4 2026 | PPO |  |  |  | EU/UNDP |  |  |  | *Donor funds |  |  |  | 10,800 |  |  |  |
| 1.1.4.3. Organisation of training and promotion of the Public Procurement Portal regarding its new functionalities |  | Q4 2026 | PPO |  |  |  | EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 960 |  |  |  |
| SPECIFIC OBJECTIVE 1.2: WIDER APPLICATION OF ENVIRONMENTAL AND SOCIAL ASPECTS AND TECHNIQUES AND INSTRUMENTS IN PUBLIC PROCUREMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  | Baseline year |  | Target value 2026 |  |  |  |
| Total number of public procurement procedures with environmental criteria |  | Number |  |  |  | Annual Report on Public Procurements of the PPO |  |  |  | 3,415 |  |  | 2025 |  | 3,450 |  |  |  |
| Total number of public procurement procedures with social criteria |  | Number |  |  |  | Annual Report on Public Procurements of the PPO |  |  |  | 363 |  |  | 2025 |  | 370 |  |  |  |
| Total number of techniques and instruments used in public procurement procedures |  | Number |  |  |  | Annual Report on Public Procurements of the PPO |  |  |  | 455 |  |  | 2025 |  | 460 |  |  |  |
| Measure 1.2.1: Strengthening the regulatory and institutional framework for green public procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: PPO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  |  | Measure type: Informative-Educational |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| Revenues from the budget/regular allocations. |  |  |  | 0612/0001 |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| *Donor funds |  |  |  | / |  |  |  |  | 3,480 |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  | Baseline year |  | Target value 2026 |  |  |  |
| Annual number of training sessions organised on public procurement procedures with environmental aspects |  | Number |  |  |  | Annual Report on Public Procurements of the PPO |  |  |  | 3 |  |  | 2025 |  | 2 |  |  |  |
| Annual number of practical tools developed (guidelines, manuals, or model tender documentation) for green public procurement |  | Number |  |  |  | Annual Report on Public Procurements of the PPO |  |  |  | 5 |  |  | 2025 |  | 2 |  |  |  |
| Name of the activity |  | Deadline for completion of activities | Institution responsible for implementation |  |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |  |
| 1.2.1.1. Development of model tender documents for green public procurement |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 1,500 |  |  |  |
| 1.2.1.2. Market research and analysis of the application of environmental aspects in public procurement procedures, with recommendations for further improvement of the regulatory framework for green public procurement |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 1,500 |  |  |  |
| 1.2.1.3. Organisation of training on green public procurement |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | *Donor funds |  |  |  | 480 |  |  |  |
| Measure 1.2.2: Promoting the application of social aspects in public procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: PPO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  |  | Measure type: Informative-Educational |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| Revenues from the budget/regular allocations. |  |  |  | 0612/0001 |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| *Donor funds |  |  |  | / |  |  |  |  | 11,480 |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  | Baseline year |  | Target value 2026 |  |  |  |
| Annual number of training sessions organised on public procurement procedures with social aspects |  | Number |  |  |  | Annual Report on Public Procurements of the PPO |  |  |  | 2 |  |  | 2025 |  | 1 |  |  |  |
| Annual number of training sessions organised on public procurement procedures with social aspects |  | Number |  |  |  | Annual Report on Public Procurements PPO |  |  |  | 2 |  |  | 2025 |  | 1 |  |  |  |
| Name of the activity |  | Deadline for completion of activities | Institution responsible for implementation |  |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |  |
| 1.2.2.1. Development of model tender documents with application of the social concept |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 1,000 |  |  |  |
| 1.2.2.2. Organisation of training on public procurement procedures with social aspects |  | Q4 2026 | PPO |  |  |  | NALED SCCI |  |  |  | *Donor funds |  |  |  | 480 |  |  |  |
| 1.2.2.3. Familiarisation of key institutions in the public procurement system with examples of good practice in EU Member States on public procurement procedures with social aspects |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | *Donor funds |  |  |  | 10,000 |  |  |  |
| Measure 1.2.3: Promoting the application of techniques and instruments in public procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: PPO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  |  | Measure type: Informative-Educational |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| Revenues from the budget/regular allocations. |  |  |  | 0612/0001 |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| *Donor funds |  |  |  | / |  |  |  |  | 4,320 |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  | Baseline year |  | Target value 2026 |  |  |  |
| Annual number of training sessions organised on the application of public procurement techniques and instruments |  | Number |  |  |  | Annual Report on Public Procurements of the PPO |  |  |  | 3 |  |  | 2025 |  | 2 |  |  |  |
| Annual number of practical tools developed (guidelines, manuals, or model tender documentation) that support the application of techniques and instruments in public procurement |  | Number |  |  |  | Annual Report on Public Procurements of the PPO |  |  |  | 4 |  |  | 2025 |  | 2 |  |  |  |
| Name of the activity |  | Deadline for completion of activities | Institution responsible for implementation |  |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |  |
| 1.2.3.1. Development of model tender documents for the use of a framework agreement |  | Q3 2026 | PPO |  |  |  | EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 1,200 |  |  |  |
| 1.2.3.2. Development of model tender documents for the use of Dynamic Purchasing System |  | Q4 2026 | PPO |  |  |  | EU/UNDP |  |  |  | Budget revenues / regular allocations for salaries, appropriations 411 and 412 *Donor funds |  | 0612/0001 |  | - 1,200 |  |  |  |
| 1.2.3.3. Organisation of training to promote the use of public procurement techniques and instruments |  | Q4 2026 | PPO |  |  |  | EU/UNDP |  |  |  | *Donor funds |  |  |  | 960 |  |  |  |
| 1.2.3.4. Analysis of the regulatory framework for the procurement of research and development (R&D) and innovation, with guidelines for practical application |  | Q4 2026 | PPO |  |  |  | EU/UNDP |  |  |  | *Donor funds |  |  |  | 960 |  |  |  |
| SPECIFIC OBJECTIVE 1.3: REDUCING THE RISK OF IRREGULARITIES IN PUBLIC PROCUREMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator(s) at specific objective level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  | Baseline year |  | Target value 2026 |  |  |  |
| Total number of procedures monitored |  | Number |  |  |  | Report on monitoring |  |  |  | 835 |  |  | 2025 |  | 850 |  |  |  |
| Total number of entities subject to regular monitoring of contract performance |  | Number |  |  |  | Annual Activity Report of the Budget Inspection |  |  |  | 80 |  |  | 2025 |  | 82 |  |  |  |
| Measure 1.3.1: Strengthening the monitoring and control of procurements below the thresholds to which the Law on Public Procurement does not apply |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: PPO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  |  | Measure type: Institutional-Managerial-Organisational |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| Revenues from the budget/regular allocations. |  |  |  | 0612/0001 |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| *Donor funds |  |  |  | / |  |  |  |  | 22,400 |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  | Baseline year |  | Target value 2026 |  |  |  |
| Annual number of monitored entities where procurements below the thresholds of application of the Law on Public Procurement have been subject to control |  | Number |  |  |  | Report on monitoring |  |  |  | 22 |  |  | 2025 |  | 24 |  |  |  |
| Name of the activity |  | Deadline for completion of activities | Institution responsible for implementation |  |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |  |
| 1.3.1.1. Analysis of irregularities constituting grounds for misdemeanour liability |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | *Donor funds |  |  |  | 1,200 |  |  |  |
| 1.3.1.2. Familiarisation of key institutions in the public procurement system with good practices in EU Member States in monitoring and e-procurement |  | Q4 2026 | PPO |  |  |  | EU/UNDP |  |  |  | *Donor funds |  |  |  | 10,000 |  |  |  |
| 1.3.1.3. Familiarisation of key institutions in the public procurement system with good practices in EU Member States in preventing corruption |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | *Donor funds |  |  |  | 10,000 |  |  |  |
| 1.3.1.4. Development of guidelines for prosecutors on monitoring public procurement procedures, including a model request to the PPO for the provision of necessary information |  | Q4 2026 | PPO |  |  |  | EU/UNDP |  |  |  | *Donor funds |  |  |  | 1,200 |  |  |  |
| Measure 1.3.2: Strengthening institutional cooperation in the public procurement system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: PPO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  |  | Measure type: Informative-Educational |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| *Donor funds |  |  |  | / |  |  |  |  | 6,960 |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  | Baseline year |  | Target value 2026 |  |  |  |
| Annual number of meetings, conferences, and training sessions organised |  | Number |  |  |  | Annual Report on Public Procurements of the PPO |  |  |  | 15 |  |  | 2025 |  | 15 |  |  |  |
| Name of the activity |  | Deadline for completion of activities | Institution responsible for implementation |  |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |  |
| 1.3.2.1. Organisation of a workshop to align the positions of the PPO, RC, MoF, and other key public procurement institutions regarding the application of the PPL |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | *Donor funds |  |  |  | 480 |  |  |  |
| 1.3.2.2. Organisation of training sessions for representatives of the MoF – Budget Inspection on the application of public procurement legislation |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | *Donor funds |  |  |  | 1,200 |  |  |  |
| 1.3.2.3. Organisation of training for representatives of the police and prosecution |  | Q4 2026 | PPO |  |  |  | EU/UNDP |  |  |  | *Donor funds |  |  |  | 960 |  |  |  |
| 1.3.2.4. Organisation of training for representatives of misdemeanour courts |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | *Donor funds |  |  |  | 960 |  |  |  |
| 1.3.2.5. Organisation of working meetings to enhance cooperation between the PPO and APC on the application of public procurement legislation |  | Q4 2026 | PPO |  |  |  | EU / NALED |  |  |  | *Donor funds |  |  |  | 960 |  |  |  |
| 1.3.2.6. Organisation of a working consultation and exchange of views with key institutions on the protection of competition in public procurement procedures |  | Q4 2026 | PPO |  |  |  | NALED |  |  |  | *Donor funds |  |  |  | 1,200 |  |  |  |
| 1.3.2.7. Organisation of a working meeting between the representatives of the PPO and the Administrative Court |  | Q4 2026 | PPO |  |  |  | EU/UNDP NALED |  |  |  | *Donor funds |  |  |  | 1,200 |  |  |  |
| Measure 1.3.3: Enhancing the quality of contract management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: MoF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  |  | Measure type: Informative-Educational |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| *Donor funds |  |  |  | / |  |  |  |  | 1,480 |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  | Baseline year |  | Target value 2026 |  |  |  |
| Annual number of training sessions on contract performance |  | Number |  |  |  | Annual Activity Report of the Budget Inspection |  |  |  | 4 |  |  | 2025 |  | 4 |  |  |  |
| Name of the activity |  | Deadline for completion of activities | Institution responsible for implementation |  |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |  |
| 1.3.3.1. Organisation of training sessions on contract performance |  | Q4 2026 | MoF |  |  |  | UNDP |  |  |  | *Donor funds |  |  |  | 480 |  |  |  |
| 1.3.3.2. Development of guidelines for contract management for contracting authorities |  | Q4 2026 | PPO |  |  |  | EU/UNDP |  |  |  | *Donor funds |  |  |  | 1,000 |  |  |  |
| Measure 1.3.4: Strengthening the institutional capacities of the Ministry of Finance Budget Inspection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution responsible for implementation (coordination of implementation) of the measure: MoF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation period: 2026 |  |  |  |  |  |  |  |  |  | Measure type: Institutional-Managerial-Organisational |  |  |  |  |  |  |  |  |
| Sources of funding for measure |  |  |  | Link to the programme budget |  |  |  |  | Estimated total funding in RSD 000 |  |  |  |  |  |  |  |  |  |
| *Donor assistance |  |  |  | / |  |  |  |  | 960 |  |  |  |  |  |  |  |  |  |
| Indicator(s) at measure level (outcome indicator) |  | Unit of measure |  |  |  | Source of verification |  |  |  | Baseline value |  |  | Baseline year |  | Target value 2026 |  |  |  |
| Total number of staff in the Ministry of Finance - Budget Inspection |  | Number |  |  |  | Information Booklet |  |  |  | 45 |  |  | 2025 |  | 45 |  |  |  |
| Name of the activity |  | Deadline for completion of activities | Institution responsible for implementation |  |  |  | Partners in the realisation of the activities |  |  |  | Estimated total financial resources by source in RSD 000. |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Source of funding |  | Link to the programme budget (PR- PA/ PJ) |  | 2026 |  |  |  |
| 1.3.4.1. Organisation of training for staff of key public procurement institutions on EU Member States’ good practices in monitoring contract performance |  | Q4 2026 | PPO, MoF |  |  |  | EU/UNDP |  |  |  | *Donor assistance |  |  |  | 960 |  |  |  |

IV. ESTIMATED TOTAL FINANCIAL RESOURCES REQUIRED FOR THE IMPLEMENTATION OF THE ACTION PLAN FOR 2026

Funds required for the implementation of activities planned under this Action Plan are provided by the 2026 Budget System Law (“Official Gazette of the RS”, No. 108/25), in Section 52 – Public Procurement Office (public funds beneficiary user code 41200), Programme 0612 – Development of the System and Protection of Rights in Public Procurement, Function 410 – General Economic, Commercial and Labour Affairs, Programme Activity 0001 – Development and Monitoring of the Public Procurement System, from financing source 01 – General revenues and budget revenues in the form of regular allocations for employee salaries from the Budget of the Republic of Serbia.

Funds totalling 77,820,000.00 dinars are envisaged as assistance from international organisations (UNDP, NALED, etc.) through projects that are either in the contracting phase or under implementation, and are not recorded in the budget as separate sources of financing

Funds required for the implementation of the activities envisaged in this Plan, under the responsibility of the Ministry of Economy, are secured by the 2026 Budget Law of the Republic of Serbia (“Official Gazette of the RS”, No. 108/25), in Section 21 – Ministry of Economy, under Programme/Programme Activity 1508/0002 – for staff salaries.

Funds required for the implementation of activities foreseen in this Plan, under the responsibility of the Ministry of Finance, will be provided as support from international organisations.

V. INFORMATION ON CONDUCTED CONSULTATIONS

During the drafting of the Proposal for the Action Plan for 2026, the Public Procurement Office began preparing the Action Plan for the implementation of the Public Procurement Development Programme in the Republic of Serbia for the period 2024–2028, starting in the third quarter of 2025. As part of the consultation process, from 25 September to 3 October 2025, interested parties were able to offer comments, proposals, and suggestions on the Proposal via email or through the “e-Consultations” Portal. Additionally, a round table was organised in Belgrade on 25 September 2025, during which the Proposal for the Action Plan for 2026 for the implementation of the Public Procurement Development Programme in the Republic of Serbia (2024–2028) was presented. Participants had the opportunity to familiarise themselves with the objectives, measures, indicators, and activities outlined in the Proposal and to offer comments, with the aim of producing a higher-quality document. At the round table, in addition to representatives of the Public Procurement Office, the organisers, and the expert engaged in drafting the Proposal, participants also included representatives from: the Republic Commission for the Protection of Rights in Public Procurement Procedures, the Commission for the Protection of Competition, the Agency for the Prevention of Corruption, the State Audit Institution, the Administrative Court, the Ministry of Finance – Budget Inspection, the Ministry of Defence, the Ministry of Internal Affairs, the Ministry of Public Administration and Local Self-Government, the Administration for Joint Affairs of Republic Bodies, the Administration for Joint Affairs of Provincial Bodies, the Standing Conference of Towns and Municipalities, and the Chamber of Commerce of Serbia.

The Public Procurement Office conducted a public discussion on the Proposal for the Action Plan for 2026 for the implementation of the Public Procurement Development Programme in the Republic of Serbia for the period 2024–2028 from 4 to 24 December 2025.

VI. FINAL SECTION

The Action Plan for 2026 forms an integral part of the Public Procurement Development Programme in the Republic of Serbia for the period 2024–2028.

This Action Plan shall be published on the Government’s website, on the e-Government Portal, and on the website of the Public Procurement Office within seven working days of its adoption.

It shall also be published in the “Official Gazette of the Republic of Serbia”.

05 Number:

In Belgrade, 5 March 2026

GOVERNMENT

PRIME MINISTER

Prof. Dr Đuro Macut

Data from the Notices of Concluded Contracts published up to 31 December 2025